## Slide 1: Module 3: Session 3
BUDGETARY CONTROL AND MANAGEMENT

## Slide 2: Session objectives
Understanding the connection between implementation and the budget in measuring performance.

## Slide 3: What is budget control?
Ensuring that implementation corresponds to plans: objectives, outputs, timing, outcomes, costs and ensuring that the profit motive is not undermined.
Note all variances directly affect profit, unfavourable ones should be minimised
Identifying deviations and making corrective decisions
Finding out why the deviation? Who is responsible? Is it controllable? What needs to be done?

## Slide 4: Common Variances
A variance is the difference between planned and actual results. Such a difference is the total variance for that budget line.
A variance is either favourable or adverse (unfavourable).
Total variance is broken down into three common variances:
  Volume
  Usage or efficiency
  Price or rate
Total variance = (volume + usage + efficiency variances).

## Slide 5: Volume variance
Difference due to actual output differing from planned output valued at the budgeted rates. For example if we planned to do 24kms of road but we actually do 20kms, the volume variance is 4kms.
  Revenue volume variance would be 4kmsx450m= 1,800m(A)
  Material volume variance would be 4kmsx8,000tonesx24,000 = 768m(F)
  Labour Volume variance would be 4kmsx72m= 288m(F)
  Fuel volume variance would be 4kmsx9,000ltrsx3,500= 126m(F)
Volume variance is the budgeted revenue/costs for actual work done as compared with the total work budgeted.
The net volume variance therefore is the budgeted profit lost due to non performance (or earned due to additional work done).

## Slide 6: Usage/efficiency variance
Usage variance arises due to used material for actual output differing from that expected valued at the budgeted cost. (expected Q – actual Q)x budgeted cost
Efficiency variance arises due to used time for actual output differing from that expected, valued at the budgeted rate. (expected hrs – actual hrs)x budgeted rate
Favourable means economy or efficiency when adverse means wastage or inefficiency.

## Slide 7: Price/rate variance
A price variance is caused when the price of the inputs differs from that budgeted for. (budgeted price – actual price)x actual quantity.
A rate variance arises when the rate of labour or hire inputs differs from that budgeted for. (budgeted rate – actual rate)x actual time.
A price variance also arises on revenue when sales price (or rate) differs from budgeted price (or rate).

## Slide 8: Interpretation of variances and their implications
Variance may be in terms of comparing budget outputs and unit cost with actual outputs and unit costs
Analysis is to determine the cause of the variance, responsibility centre and develop corrective action
Action may be to change course, promote the variation or do nothing

## Slide 9: Variances and corrective action
During variance analysis focus on controllable elements e.g. to focus on the prices variance of electricity will be futile whereas electricity usage variance is controllable.
To be effective, administrators should identify the budget items they can control versus those they can't.
Variances could be interlinked, look out for the linkage e.g. a favourable material price variance could be linked to an adverse material usage variance and an adverse labour efficiency variance if the material bought was substandard!

## Slide 10: Work variations and variance analysis
Contract Variation is most often when some extra work gets added to a project after the contract has been signed.
Such additions form volume variances
An expenditure variation is due to any change from the original scope of works and extra income could be sought for this expense.

## Slide 11: Variance analysis summary.
Determine the variance say in labour, materials, overheads
Investigate possible cause of variances
Propose and implement corrective action.

## Slide 12: Group activity: Expenditure
Revenue source | yr1 | yr2 | yr3 | yr4 | yr5
Contract one |  |  |  |  | 
Contract two |  |  |  |  | 
Contract three |  |  |  |  | 
Total |  |  |  |  | 

## Slide 13: Group activity: expenditure variances
Particulars | Budgeted | Six month budget | Actual six months | variance | comment
Materials |  |  |  |  | 
Labour |  |  |  |  | 
Administration and overheads |  |  |  |  | 
Construction |  |  |  |  | 
Total |  |  |  |  | 

## Slide 14: Group presentations
Using the budget developed from the previous session and the actual performance provided, find out the causes of cost variances and suggest persons responsible.
Develop a simple control budget for Munaku. Use the control budget to propose a budget for 5kms of road done.