## Slide 1: CONTRACTS
Module Six: Session 4

## Slide 2: Objectives of the Session
Appreciate the concept of contracts as it relates to the road sector
List and discuss the key elements of a contract
List the different types of contracts in the road sector
Explain the importance of having a signed contract

## Slide 3: Road Contracts
Contract means an agreement between a PDE and a provider,
Results from the application of the appropriate and approved procurement procedures,
Concluded following a bid award decision of a Contracts Committee or any other appropriate authority.

## Slide 4: GENERAL CONDITIONS OF A CONTRACT
- These contain standard provisions that remain unchanged – provisions used without modifying their text such as:
Scope and method of work for different works items such as shoulder grading, re-gravelling, premix pothole patching, repair of edges etc.
Measurement of works and payment terms
Definitions, interpretations and definition of risks etc.
Time and quality control provisions
Cost control and payment related provisions
Completion, termination or take over of works etc..

## Slide 5: SPECIAL CONDITIONS OF CONTRACT
- These specify key clauses unique to the contract like:
  Commencement and completion dates
  Defects liability period
  Description of works
  Payment schedule and period
  Performance security etc..

## Slide 6: CONTENT OF A CONTRACT
Procurement reference
Parties to the contract
Agreement clause stating work and consideration
Signature of employer and contractor
Signature of witnesses for each
Attachments that form part of the contract
  Clearance from Solicitor General
  Site visit certificate works program
  Contracts Committee Approval
  Letter of notification of award
  General and special contract terms etc.
Notes: DG Note:
What is meant by Contract Form? Is it just the Contract?

## Slide 7: Contract Documents that normally form part of a contract
The documents forming the Contract are interpreted in the following order of priority;
    Agreement,
    Letter of award notification and acceptance thereof,
    The Provider’s Bid, as amended by any clarifications, negotiation.
    Special Conditions of Contract(SCC),
    General Conditions of Contract (GCC),
    Statement of Requirements,
    Any other document listed in the SCC as forming part of the Contract. (see slide 6)

## Slide 8: What constitutes a contract?
Essential elements in a contract are:
Intention to enter into a legally binding agreement.
Agreement between parties (offer and acceptance).
Consensus about the subject matter
Both parties must provide a consideration.
Parties must have legal capacity to contract.

## Slide 9: Types of Contracts
Lump sum contract
Time based contracts
Ad measurement
Framework Contracts
Percentage Contracts
Petty Contracts
Cost Reimbursable contracts.
Target Price Contracts
Retainer Contracts.
Contingency or Success Fee.
A combination
Notes: DG Notes:
Items f, g, h, i, j and k are not not described anywhere?
Is C) (Ad measurement) a re-measured contract?

## Slide 10: Lump sum contract
This a contract with a pre agreed price for performance of the specified tasks.
The amount of the price is based on the deliverables and is fixed.
Such a contract passes the risk of the cost of works to the provider.
An example is where a bidder contracts to grade a road at a fixed fee of xm shillings.

## Slide 11: Time based contract
A time based contract is one where the provider is remunerated on time taken to do a task.
A rate is agreed but the time is uncertain
It is common where the scope and duration of the works are difficult to ascertain
It requires close supervision to ensure that work is going on when it should
It is good when the provider is good, competent and ethical,

## Slide 12: Ad measurement contract
The unit rate is agreed for the tasks and measurements of tasks done over the period and paid for at the standard rate.
Good where:
  works cannot be ascertained with accuracy, or
  is likely to have unforeseen works conditions,
  but where output is easily measurable.
Costs remain uncontrollable and the risk of cost variation is born by the PDE,
An example is excavation of soil/gravel

## Slide 13: Percentage contract
Remuneration to the provider is based on an agreed percentage to the cost incurred
Eg a professional fee of 5% on cost.
This work well where the contractor is experienced and cost cautious.
It offers no incentive for the provider to save,

## Slide 14: Framework contracts
Apply to tasks that are recurring over a period of time.
A unit rate is agreed for the tasks.
The contract is valid for a period of time say three years.
The provider is asked to carry out the contracted tasks as and when they are needed, value the work done and paid accordingly
The practice saves time and money spent on repetitive procurements.

## Slide 15: Factors considered in selecting contract type
Nature of Procurement
Minimisation of risk
Value for money
Cost control
Organizational requirements

## Slide 16: Importance of a signed contract
Documents a contractual relationship between a PDE and the contractor
Makes obligations of each party clear
Offers a basis of reference
Provides specifications
Defines basis of emoluments and payment terms
Avoids conflict and facilitates arbitration

## Slide 17: Q&A Session
State core items you expect to be included in a road works contract
Name and explain five common forms of works contract
In order of preference what documents constitute a works contract?
What legal and operational challenges have you experienced in execution of road works contracts?
Name some of the events/omission during the procurement process that could lead to invalidate a contract between a PDE and a provider.