## Slide 1: Module 1: Session 6
Financial Management Planning and Control

## Slide 2: Purpose of the Session
  Introduce the concept of budgetary planning and control
  Influence attitudes from incremental to zero or activity based budgeting.
  Demonstrate the basic application of variances and variance analysis e.g. Total, usage, efficiency and price variances.
  Introduce the value for money concept
  Indicate the common taxes that affect financial planning of contractors.

## Slide 3: What is a budget
A budget is a management tool to guide and control performance.
All activities of the business should be budgeted for and monitored.
During tendering the cost budget is a useful tool to guide tender bidding prices.
A budget, once approved, serves as a yardstick against which performance may be measured.

## Slide 4: Budgetary Control
The budgetary control process operates by comparing actual to planned performance and
  Determining the variances and their effect on results
  Interpreting the cause,
  Identifying responsibility for them.
Variance analysis helps to inform future actions and decisions e.g. future bids, remedial action, investigation etc.

## Slide 5: Approach to budgeting
Incremental Budgeting (IB) uses historical figures and apply a margin for volume and inflationary adjustments.
Zero Based Budgeting (ZBB) builds up the cost from the basic elements that make up the task. The cost budget should best be built up from the quantity surveyors’ estimates.
Activity Based Budgeting (ABB) builds up the budget based on activities that are to be performed and for each task identify the input, output, cost and outcome.

## Slide 6: Typical variances in Road Construction
Total variance is the difference between budgeted and actual expenditure
  (Budgeted cost less actual cost)
Material usage variance is the difference in the quantity of materials used at the budgeted price
  =(budgeted quantity less actual quantity )x the budgeted price.

## Slide 7: Typical variances in road construction
Material price variance is the difference in price of the actual quantity used
  =(budgeted price less actual price) X the actual quantity.
Labour or machine efficiency variance is the difference in labour or machine time at the budgeted rate
  =( budgeted time less actual time) X budgeted rate/price
Labour or machine rate variance
  =(the budgeted rate or price less the actual rate) X the actual hours taken.

## Slide 8: Responsibility for variances
It is important to investigate causes and persons responsible for variances.
Purchasers are usually responsible for price related variances and at times usage if the materials are not of the expected quality
Supervisors are usually responsible for usage and efficiency variances

## Slide 9: Responsibility for variances
Machine operators could be responsible for machine efficiency variances. However those responsible to hire or to train machine operators or to train staff could also be responsible for efficiency rates.
Persons responsible for maintenance of equipment could cause machine efficiency variances.

## Slide 10: Value for Money Concept (VfM)
  Is utilising resources most effectively and efficiently in order to get desired results of quality, cheapest and quickest.
  It involves maximizing quality obtained but minimizing input resources including time.
  Calls for stretching resources to the maximum.
  Requires focusing not only at output but also the outcome compared to the resources we expend.
  In road construction vfm means having integrity, being frugal, having speed and delivering durability.

## Slide 11: Value for money consciousness
Works should be conceived, planned, executed and evaluated for VFM, including quality and time.
Assess the output, the outcome and the resources to be consumed for VFM.
Ensure the desired output occur.
Ensure the expected outcome is realized.
Ensure the processes are cost effective.
Keep asking what could be done better if any.
Ask what else can now be done to ensure/improve the outcome.

## Slide 12: Common taxes and statutory obligations that affect costs
Trade license
Value Added Tax
Income/corporation tax
Rates
Withholding tax
PAYE
NSSF (employer contribution)
District income levy
Local services tax

## Slide 13: Group assignment
1. With ref. to case study data, suggest a simple budget for Munaku to rehabilitate 2km with 2nd grade gravel.
2. Outline the weakness of the pricing method of Munaku and analyse why Munaku did not realize his anticipated profit.
3. Using the availed budget work out the usage, price and efficiency variances and explain possible causes.
4. Explain what you understand by value for money and why a road contractor should aspire to deliver value worthy.
5. Identify possible taxes levied on a tax contractor and show how they relate to contract costing.
All agree on actionable points.

## Slide 14: END
Q&A

## Slide 15: 2kms incremental budget
Munaku's Incremental bid | 
Historical cost | 210,000,000
Economic mark up 30% | 63,000,000
Expected cost | 273,000,000
Margin 30% | 81,900,000
Price | 354,900,000
Rounded up | 355,000,000

## Slide 16: 2kms Zero Based Budget
 | Ideal Zero Based Budget bid |  | 
Item | cost per unit | Quantity | Cost
Materials: Gravel in tonnes | 5,000 | 20,000 | 100,000,000
Machine hire in hours | 400 | 200,000 | 80,000,000
Fuel for machines in lts | 40,000 | 3,000 | 120,000,000
Direct labour (man days) | 900 | 10,000 | 9,000,000
Supervision (man months) | 4 | 500,000 | 2,000,000
Total cost |  |  | 311,000,000
Margin 30% |  |  | 93,300,000
Bid price |  |  | 404,300,000
Costs underestimated by 14% and bid price understated by 12% |  |  | 

## Slide 17: Variances and persons responsible
 | Usage | Price | Efficiency | Total
Gravel | (100,000,000) | 20,000,000 |  | (80,000,000)
Machine |  | - | 16,000,000 | 16,000,000
Fuel | (18,000,000) | (5,700,000) | 24,000,000 | 300,000
Labour |  | (7,500,000) | (6,000,000) | (13,500,000)
Total cost variance | (118,000,000) | 6,800,000 | 10,000,000 | (77,200,000)
Budgeted profit |  |  |  | 93,300,000
Actual profit |  |  |  | 16,100,000
 | Responsibility for variance |  |  | 
Variance due to machine operator |  |  | 40,000,000 | 
Variancence due to Purchaser |  |  | 6,800,000 | 
Variance due to supervisors |  |  | (124,000,000) | 
Total profit variance |  |  | (77,200,000) |